## Sheet1
PHASE | TASK | SIZE MEASURE | TYPICAL EFFORT PER SIZE MEASURE (PERSON / HOURS) | SIZE | EFFORT (PERSON / HOURS) | EFFORT (PERSON / HOURS) |  | Final (Fibonacci)
Expert A Expert B
Requirements | Definition of Users and User Roles | # roles | 0.2 | 5 | 1 | 1 | 1 | 1
| Definition of Scope and Limitations | # attributes | 0.15 | 6 | 0.9 | 1 | 0.75 | 1
| System Requirements Specification | # requirements | 0.5 | 8 | 4 | 4.5 | 4 | 5
Configuration Management | Configuration Items List | # CI items | 0.15 | 13 | 1.95 | 2 | 1.5 | 2
Estimation | Estimation Record | # tasks | 0.15 | 13 | 1.95 | 1.5 | 1.75 | 2
Design | State Transition Diagram | # states | 0.25 | 4 | 1 | 1 | 1.25 | 2
| Definition of Use Cases | # use cases | 1 | 4 | 4 | 4 | 5 | 5
| Definition of Fields | # fields | 0.15 | 20 | 3 | 2.75 | 3.25 | 5
| Definition of Reports | # reports | 1.5 | 2 | 3 | 2.5 | 3 | 3
Peer Reviews | Issues from Peer Reviews | # issues | 0.25 | 4 | 1 | 1 | 0.5 | 1
Implementation | Defect Tracking System | # tables & forms | 7 | 7 | 49 | 50 | 48 | 55
Test Design | Test Cases | # test cases | 0.4 | 8 | 3.2 | 4 | 3.5 | 5
Test Execution | Record Defects Identified During Testing | # defects | 0.3 | 8 | 2.4 | 2.5 | 3 | 3
TOTAL | [7 empty] | 90